# GROSSMONT-CUYAMACA COMMUNITY COLLEGE DISTRICT

# EMPLOYMENT SERVICES

FACULTY * #r-02XXX  *  COLLEGE

SAMPLE RECRUITMENT TIMELINE

COMMITTEE CHAIRS:

| September 15, 2025 | - Strategic Hire Forms approved and sent to DBC |
| --- | --- |
| September 15, 2025 | - Committee chair submits committee formation request here |
| October 3, 2025 | - Committee members appointed and HR notified for each recruitment |
| Week of October 6, 2025 | - Recruiter works with committee chair to schedule orientations |
| Week of October 27, 2025 | - Committee Orientations (via Zoom, all committee members must be present) - Committee develops job description/announcement, finalizes timeline |
| November 10, 2025 – January 12, 2026 | - Public Announcement Period (minimum 30 calendar days) - Identify outreach to ensure a diverse pool |
| December 1, 2025 | - Finalized Selection Plan, Presentation Prompt, and Interview Questions due to HR (must be completed before candidates are moved forward for committee screening in Workday) |
| January 12 – 23, 2026 | - HR processes applications |
| All committee members MUST be up-to-date with HIRE Training by January 12, 2026 |  |
| January 26 – February 6, 2026 | - Committee Begins/Completes Paper screening Process |
| Week of February 9, 2026 | - Committee meets to select applicants to be interviewed (one-hour meeting on Zoom) |
| Monday, February 23 (9am-5pm) Tuesday, February 24 (9am-5pm) Wednesday, February 25 (9am-5pm) | - Tentative Interview Date(s) Depending on Number of Candidates (minimum of one week after candidates are selected) - In-person interviews; candidates have a Zoom option |
| After interviews are complete and ratings are submitted Via Zoom (Day of) | - Committee Interview Wrap Up Meeting |
| March 11 – 18, 2026 | - Final Interviews (minimum of one week after committee wrap-up) |
|  | - Reference Checks Completed by committee chair and Submitted to HR |
| March 30, 2026 | - Recommended Candidate Forwarded for Chancellor’s Approval |
| No later than April 6, 2026 | - Candidate Offer Made |
| August 17, 2026 | - Start Date for Selected Candidate |

Note:  Above dates may vary depending on availability of all committee members.