Memorandum of Understanding (MOU) Approval and Implementation Process

1. Initiation Phase

Goal: Ensure all relevant interest holders are identified and included early.

Steps:

- Proposal Submission:

- MOU proposals may be initiated by an Administrator, faculty member, department. Proposal shall clarify the need and impact on students, employees and staff, and/or campus (Cost/Benefit Analysis).

- The initiating party submits a preliminary concept summary to the District liaison

- Interest Holder Identification & Notification:

- Before formal drafting begins, the following individuals must be notified and included in the initial discussion:

- Presidents

- Vice Presidents, Student Services

- Vice Presidents, Instruction/Academic Affairs

- CPIE Deans

- Academic Senate Presidents (both campuses)

- District Representatives such as AVC, Educational Support Services and AVC, Technology

- These individuals will help determine which additional faculty, Deans, or Department representatives should participate in the development of the MOU

- Initial Consultation Meeting:

- Convened by the District liaison.

- Purpose: Clarify intent, identify affected programs, and define college-level impacts, capacity, and implementation needs as well as develop expectations for specific areas and roles.

2. Drafting Phase

Goal: Develop the MOU collaboratively with input from those responsible for implementation.

Steps:

- College-Level Outlining Teams:

- Each college forms a small MOU Proposal Review and Response  team including faculty and administrators who will implement the agreement. The team will outline college needs, priorities, and intended parameters to present to the District drafting team along with an intended college implementation plan.

    - Initial Implementation Plan will consider and outline the following

- Key activities and responsibilities

- Timeline and milestones

- Resource or staffing needs

- These teams ensure the outline  reflects college-specific needs, capacity considerations, and operational realities.

- Cross-College Coordination:

- The District liaison facilitates communication between colleges to ensure alignment and to address  any differences in approach or capacity.

- District Drafting Process:

  - The District drafting team receives college outlines and develops an initial draft to reflect college feedback is consolidated by the District liaison for incorporation into the final draft.

    - The completed draft is submitted to the initial consultation team for review and feedback, and considerations for implementation.

- Review by Key Stakeholders:

- The draft MOU is reviewed by:

- Presidents Cabinets

- Academic Senates

- Chancellor's Cabinet

- Any other appropriate Council or Committee as determined by the College Interest holder

- Feedback is consolidated by the District liaison for incorporation into the final draft.

3. Approval Phase

Goal: Secure formal approval through shared governance and administrative channels.

Steps:

- College-Level Approval:

- Each college follows its internal governance process for review and approval (e.g., Curriculum Committee, Academic Senate, College Council).

- District-Level Review:

- Once college approvals are complete, the MOU is forwarded to the District for legal, policy, and compliance review.

- The District ensures that the MOU aligns with district-wide policies.

- Final Authorization:

- After District review, the MOU is signed by appropriate College and/or District representatives.

4. Implementation Phase

Goal: Ensure implementation is led by the Vice Presidents responsible areas needed for execution at the college level.

Steps:

- College Implementation Plans:

- Each college develops a finalized detailed implementation plan, led by the department or division responsible for the MOU’s activities.

- The plan will clarify :

- Key activities and responsibilities

- Timeline and milestones

- Resource or staffing needs

- District Coordination:

- The District liaison supports coordination across colleges and ensures consistency where appropriate (e.g., data reporting, legal compliance).

- The liaison does not direct campus-level operations but facilitates communication and resource sharing.

5. Monitoring and Review Phase

Goal: Maintain transparency and accountability while allowing for course correction.

Steps:

- Annual Check-In:

- Each college provides an update on progress, challenges, and outcomes.

- The District liaison compiles updates for district-wide review.

- Revision and Renewal:

- MOUs are revisited on a defined schedule (e.g., every 3 years) to ensure ongoing relevance.

- Revisions follow the same inclusive process as original development.